## Team
Initials | First | Last | Email | GitHub Username
hd | Hunter | Devlin | hdevlin@stevens.edu | hdevlin
lo | Leo | Ouyang | louyang2@stevens.edu | ruglord
nc | Nicholas | Cacchione | cacchionen@yahoo.com | NickCacchione
|  |  | GitHub Repository: | https://github.com/hdevlin/GEDCOM

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | hd | Coding
1 | US02 | Birth before marriage | hd | Coding
1 | US03 | Birth before death | lo | Coding
1 | US04 | Marriage before divorce | lo | Coding
1 | US05 | Marriage before death | nc | Coding
1 | US06 | Divorce before death | nc | Coding

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2019-02-19 | 24 |  | 0

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | hd | Coding | 100 | 20 | 120 | 90
US02 | Birth before marriage | hd | Coding | 100 | 10 | 120 | 90
US03 | Birth before death | lo | Coding | 100 | 10 | 120 | 90
US04 | Marriage before divorce | lo | Coding | 100 | 10 | 120 | 90
US05 | Marriage before death | nc | Coding | 100 | 11 | 121 | 90
US06 | Divorce before death | nc | Coding | 100 | 12 | 122 | 90

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Unique IDs | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Include input line numbers | List all living people over 30 who have never been married in a GEDCOM file
US15 | Include partial dates | List all multiple births in a GEDCOM file
US16 | Reject illegitimate dates | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US17 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US18 | Multiple births <= 5 | No more than five siblings should be born at the same time
US19 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US20 | Male last names | All male members of a family should have the same last name
US21 | No marriages to descendants | Parents should not marry any of their descendants
US22 | Siblings should not marry | Siblings should not marry one another
US23 | First cousins should not marry | First cousins should not marry one another
US24 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews